## Sheet1
Alexander Partridge
2018-03-20
CS406
Risk Management:
Five Risks for SAMS
RISK | RESOLUTION MEASURES | JUSTIFICATION
Scope is poorly defined | Early in development, take time to analyze and document requirements. | Scope must be nailed down early in development so scope creep is not an issue.
Unrealistic deadlines | As this is the first project for the project manager, there is a chance that the schedule is overly optimistic. Getting feedback from the team of developers early on will be important. | By consulting all developers, the schedule will be most accurate.
Imbalanced workload shared among developers | One of the risks of any team is that one developer may take on the brunt of the work. Making sure everyone has clear lines of communication with each other and management can combat this risk. | Work responsibilities are distributed responsibly with clear communication so that no task goes undone and no one person has the brunt of the work.
Personnel shortfalls | As a three-person development team, each person must carry their own weight. If they are inexperienced the project could easily fall behind. An interview process can combat this problem. | By interviewing potential developers, we can be sure to hire those with qualifications that match the task.
Gold-plating | This is a relatively simple project so it’s important to stay focused on the requirements. Communicating current projects and what requirements they relate to periodically will help. | Simple tasks like the ones required for this system can leave over-ambitious developers bored. By communicating daily workload and how it relates to requirements is the best way to ensure each developer is on track.